## Before covid
Date commencing | 2020-02-25 | 2020-03-02 | 2020-03-09 | 2020-03-16 | 2020-03-23 | 2020-03-30 | 2020-04-06 | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04
Week of project | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Task at hand
Group checkpoints
management | 2020-02-25: Project outline; 2020-03-02: Proposal; 2020-03-09: Code of conduct; 2020-03-16: Risk+doc; 2020-03-23: Risk+doc
testing | 2020-03-02: Mission research; 2020-03-09: Test research; 2020-03-16: Test research; 2020-03-23: Baseline testing; 2020-03-30: Efficiency testing
ideation | 2020-02-25: Project outline; 2020-03-02: Mission research; 2020-03-09: Finding sources; 2020-03-23: Finishing touches
design | 2020-03-02: Mission research; 2020-03-16: Algorithm search; 2020-04-06: Finishing touches
api | 2020-02-25: Project outline; 2020-03-02: Mission research
gui | 2020-03-02: Mission research
baseline | 2020-02-25: Project outline; 2020-03-02: Mission research; 2020-03-09: Partial setup; 2020-03-16: Working setup; 2020-03-23: Finishing touches
maths | 2020-03-02: Mission research; 2020-03-09: Work along actual iterative project
iterative | 2020-03-02: Mission research; 2020-03-09: Dataset matching; 2020-03-16: Settle algorithm
|  | Mission research | Dataset matching | Testing options
|  |  | 10/03 mentor |  | 24/03 mentor
Gabriel | bar: 2020-03-02
Sebastian | bar: 2020-03-02
Brendon | bar: 2020-03-02
Mircea | bar: 2020-03-02
Group | bar: 2020-03-02
Date of meeting | 2020-02-25: 19/02; 2020-03-02: 2020-02-25; 2020-03-09: 2020-03-03; 2020-03-23: 2020-03-10; 2020-04-06: 2020-04-05
|  | ideas | gantt chart |  | settled on theme |  | 1pm- 3pm
|  | missions | checkpoints |  | video research |  | got github working
|  | proposal review | dataset search |  | algorithm search |  | Mircea got Anaconda
|  |  | algorithm doc |  | new task: advanced gantt |  | installing keras
|  |  | github setup |  | api reseach |  | opencv
[5 empty] | agreed to delay until |  | tkinter
|  |  | add "stuff we tried" |  | intelligent systems is finished |  | tensorflow
|  |  | document the process |  |  |  | coronavirus
|  |  | YOLO + SSD |  |  |  | boosted to a meeting every other day
enhance existing solutions

## After Covid
date | 2020-04-13 | 2020-04-20 | 2020-04-27 | 2020-05-04 | 2020-05-11 | 2020-05-18 | 2020-05-25 | 2020-05-28
Ideation | [7 empty] | final touches
Solution | [7 empty] | final touches
Baseline | find new dataset | setup detection in one file | setup environment | setup training |  |  |  | final touches
Testing | [7 empty] | final touches
Management | [7 empty] | final touches
Mathematical |  | evaluate detection |  | evaluate training |  |  |  | final touches
API | [7 empty] | final touches
GUI | [7 empty] | final touches
Iterative | [7 empty] | final touches